PTA PLAN OF WORK

Date Submitted:	  9/10/2021

Chairperson Name:	  Erica Hamblen

Committee Name:	  General Meeting

PROGRAM/Event Information

Name:		 1st General Meeting

Purpose:	 To vote on FY21-22 budget, bring members together

Date:		 Tuesday, 9/14/21

Place/Time:     Pavilion @ 5:30 p.m. for dinner, meeting beings at 6:00 p.m.

PLANNING MEETING INFORMATION

Date/Time: 	  9/10/2021

Place:		September board meeting

- Erica H. will make sure members are notified of the meeting in the PTSA parent pack sent home the 2nd week of school

  - MH blast will be sent one week prior

  - Announce in Memberhub and make sure it is in our calendar, website, etc.

- Erica H. will send out agenda, budget and prior minutes to those who register by Sunday. 9/12

  - Erica H. will make sure to have a script ready for Sarah regarding the proper procedure to vote

- Sarah will make sure minutes are approved & get Erica H. agenda by 9/10

- Dinner will be Publix deli boxes:  ½ sandwich (turkey or ham choice), chips, cookie and drink included we will charge $7/box; members pay the night of

  - Erica H. will place order @ Publix on Lutz Lake Fern on Monday, 9/13 @ 10 a.m.

  - Allison_ will pick up meals at 5:00 p.m. on Tues, 9/14

  - Erica H.  will bring waters

- Erica H. will email Maylinn for her to ask the custodians to set up microphone & speaker, 3 tables and 30 chairs.

  - Tables will be for check in and setting out food, and one for meeting

- Mishell will get cash box and $50 in ones to accept payment for dinners

Est. Cost:	$50

This section completed at Executive Board Meeting

Approved Budget:

Approved by:

Date: